## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION I - ILOCOS REGION |  | CALENDAR YEAR: | 2023
PROVINCE: | PANGASINAN |  | QUARTER: | 4
CITY/MUNICIPALITY: | BALUNGAO
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
I. SOCIAL SERVICES
* Dietarty Supplementation of Expectant mothers | Balungao | 775576.8 | 2023-04-13 | 2023-12-15 | 100% | 775550 | None | Completed
* Demolation of Municipal Gym and Construction of Apolinario Mabini | Poblacion, Balungao Pangasinan | 9000000 | 2023-09-13 | 2023-11-12 | 100% | 8994144.88 | None | Completed
II . ECONOMIC SERVICES
* Establishment of Balungao Coffee Production | Poblacion, Balungao Pangasinan | 3500000 | 2023-04-21 | 2023-06-04 | 100% | 3499750 | None | Completed
* I start Program (LGU- Counterpart) | Balungao | 2000000 | 2023-04-19 | 2023-05-18 | 100% | 1999750 | None | Completed
* Establishment of Goat Academey | Balungao | 5000000 | 2023-04-17 | 2023-05-17 | 100% | 4999820 | None | Completed
*Rehabilitation of Farm to Market Road | Rajal, Balungao | 5000000 | 2023-04-17 | 2023-05-16 | 100% | 4999650 | None | Completed
III. OTHER SERVICES
* Reforestation Program | Mabini ,Balungao | 5000000 | 2023-04-13 | 2023-04-22 | 100% | 4999915 | None | Completed
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| GLORIA C. FERNANDEZ |  |  |  | MARIA THERESA R. PERALTA
| Municipal Budget Officer |  |  |  | Local Chief Executive

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v1