## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v1

## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION I - ILOCOS REGION |  | CALENDAR YEAR: | 2024
PROVINCE: | PANGASINAN |  | QUARTER: | 4
CITY/MUNICIPALITY: | BALUNGAO
PROJECTS STATUS
Project/Program/Activity Name | Location | Total Cost | Date Started | Target Completion | % of Completion | Totals Cost Incurred to Date | Number of Extention (if any) | REMARKS
I. SOCIAL SERVICES
Dietary Supplementation of Expectant Mothers & Children | Barangay Capulaan, Kita-Kita, Poblacion, Pugaro, San Joaquin, and San Raymundo of Balungao, Pangasinan | 827629.6 | April 01, 2024 | Sept. 30, 2024 | 100 | 827629.6
Energy Conservation Program for the Installation of Solar Power System at Municipal Hall, Balungao, Pangasinan | Municipal Compound, Poblacion, Balungao, Pangasinan | 999758.76 | Sept. 30, 2024 | Dec. 31, 2024 | 100 | 999758.76
Water Quality Management and Monitoring Program | Balungao, Pangasinan | 100000 | Jan. 2, 2024 | Dec. 31, 2024 | 50.05 | 50050
Purchase of Tricycle and Improvement of MRF for the Solid Waste Management Program | MRF Compound, Poblacion, Balungao, Pangasinan | 200000 | Jan. 2, 2024 | Dec. 31, 2024 | 100 | 200000
Improvement of Balungao Super Health Center | Esmeralda, Balungao, Pangasinan | 2999707.15 | Sept. 4, 2024 | Oct. 4, 2024 | 100 | 2999707.15
II . ECONOMIC SERVICES
Improvement at the Rice Processing Center III | Pugaro, Balungao, Pangasinan | 4999364.92 | May 24, 2024 | Oct. 31, 2024 | 100 | 4999364.92
Construction of Restrooms and Shower Area at Mt. Balungao Hot and Cold Spring Resort at Brgy. San Andres, Balungao, Pangasinan | Mt. Balungao Hot and Cold Spring Resort, San Andres, Balungao, Pangasinan | 3499727.85 | Sept. 16, 2024 | Oct. 31, 2024 | 100 | 3499727.85
Purchase of Materials for Construction of Comfort Room with Septic Tank for the Households at Balungao, Pangasinan | 20 Barangays of Balungao, Pangasinan | 999200 | Sept. 19, 2024 | Dec. 27, 2024 | 100 | 999200
Potable Water Supply for the Pipe Drilling & Water Supply at Brgy. San Andres, Balungao, Pangasinan | San Andres, Balungao, Pangasinan | 999705.37 | Sept. 30, 2024 | Oct. 31, 2024 | 100 | 999705.37
Water Treatment at Mt. Balungao Hot and Cold Spring Resort at Brgy. San Andres, Balungao, Pangasinan | Mt. Balungao Hot and Cold Spring Resort, Balungao, Pangasinan | 1988872 | Nov. 7, 2024 | Dec. 23, 2024 | 100 | 1988872
Conduct of Community Based Training Program | Balungao, Pangasinan | 3529.4 | June 1, 2024 | Dec. 31, 2024 | 0 | 0
Balungao Coffee Production | Balungao, Pangasinan | 750000 | Jan. 2, 2024 | Dec. 31, 2024 | 3.5835 | 26876
Goat Academy | San Andres, Balungao, Pangasinan | 500000 | Jan. 2, 2024 | Dec. 31, 2024 | 77.021 | 385105
Construction of Goat House II | San Andres, Balungao, Pangasinan | 1499871.9 | Sept. 30, 2024 | Dec. 31, 2024 | 0 | 0 |  | Suspended due to on process application of CBFMA at DENR
III. OTHER SERVICES
Rehabilitation of the Public Plaza, Parks, & Auditorium of this Municipality of Balungao, Pangasinan | Municipal Compound, Poblacion, Balungao, Pangasinan | 6999745.34 | Sept. 6, 2024 | Oct. 6, 2024 | 100 | 6999745.34
Totals |  | 27367112.29 |  |  |  | 24975741.99
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| ALMEDA O. DE VENECIA |  |  |  | MARIA THERESA R. PERALTA
| Municipal Accountant |  |  |  | Local Chief Executive